NSRC THEME 3: Forest Productivity and Forest Products

PROJECT TITLE: Managing for complexity in the Acadian Forest: influence of natural disturbance based expanding-gap silviculture on stand productivity and regeneration dynamics 20 years after two harvest entries.

PRINCIPAL INVESTIGATOR AND CONTACT INFORMATION:

Lead Principal Investigator: Robert S. Seymour, Curtis Hutchins Professor of Forest Resources (Quantitative Silviculture), School of Forest Resources, University of Maine, 5755 Nutting Hall, University of Maine, Orono, ME 04469; Tel: 207-944-9534, Fax: 207-581-2875, Email:  rseymour@maine.edu.

Co-PI: Shawn Fraver, Assistant Professor of Forest Ecosystem Science

CIs: Nathan Rutenbeck Ph.D. Candidate; David Carter, M.S. Candidate

TOTAL AMOUNT REQUESTED:

AMOUNT REQUESTED YEAR 1 (2014-2015): $28,913

AMOUNT REQUESTED YEAR 2 (2015-2016): $18,000

Theme 3 Topics Addressed Specifically:

Biological Processes: Increased understanding about the underlying biological processes driving current and future net primary productivity of Northern Forest ecosystems, including:

- Ecophysiological response of commercial tree species to silvicultural practices

- Enhances methods for assessing forest and stand productivity

- Influence of harvesting practices on genetic variation of commercial tree species

- Influence of management practices on long-term site productivity

Management: Increased understanding about the influence of management practices on productivity of Northern Forest stands, including:

- Influence of current partial harvesting practices on future regeneration and growth

- Low-cost silvicultural systems to improve species composition of natural regeneration

Prediction: Improved prediction of how changing management and environmental conditions will influence future wood supplies and forest conditions, including:

- Improving regional growth and yield simulators, such as the Forest Vegetation Simulator and other widely used models

- Improving forest inventory and monitoring systems and their use in improving prediction of current and future forest conditions at regional, state, and local levels.

- Decision support systems for large-scale pest outbreaks

- Influence of forest practices on stand and forest-level carbon dynamics

- Forest growth and species response to climate change

Project Goals and Supporting Objectives:

It is well accepted that making use of natural disturbance based silviculture (NDBS) to enhance structural heterogeneity in managed forest systems across space and time can help protect biodiversity and maintain ecosystem resilience. The tradeoffs these strategies incur in terms of traditional, fundamentally important metrics of forest management are not well understood, however. Our main goal is to quantify the effects of using novel gap-based variable retention NDBS systems to manage for forest complexity on the pattern and process of productivity and regeneration dynamics using a combination of long-term permanent plot data and newly installed monitoring efforts. Our specific objectives will center on testing the following null hypotheses regarding the productivity and competitive dynamics of regeneration and retention layers within harvest gaps:

- Survival of retention trees is not different among species, nor does it depend on spatial relationships to other residual structure.

- Growth and gas exchange rates of retention trees do not show patterns of release following harvest, regardless of species or spatial relationships to other residual structure.

- Retention tree leaf area and growth efficiency is not dependent on spatial relationships to other residual structures, and fraction of reserve tree canopy projection area to total gap area is not different from the fraction of total basal area designated for retention at the time of harvest

- Composition of regeneration in the harvest gaps is identical to the original stand, is driven entirely by the presence of advance regeneration, and is unaffected by spatial position relative to gap edges and reserve trees, regardless of reserve tree species and crown characteristics such as leaf area and canopy projection area.

- Growth, leaf area, and growth efficiency of dominant regeneration is driven entirely by neighborhood competitive dynamics, and is thus unaffected by spatial position relative to gap edges and reserve trees, regardless of reserve tree species and crown characteristics.

- Gas exchange rates of dominant regeneration following release are unaffected by spatial position relative to gap edges and reserve trees, regardless of reserve tree species and crown characteristics.

Project Justification and Relevance:

Within the last twenty years silvicultural systems designed to approximate natural disturbance regimes have been suggested as a way to simultaneously manage for biodiversity and commodities.[17,10,13] Pickett and White[15] described the disturbance regime of an ecological system as the ‘demography and dispersion of gaps’ within that system. Based on the gap-dynamics of the Acadian forest, therefore, the nationally prominent Acadian Forest Ecosystem Project (AFERP) was initiated in 1994 to test natural disturbance-based silviculture using two expanding-gap regeneration systems with structural retention.[19,20] It was postulated that such systems could sustain productivity for commodity harvests and the regeneration of desirable species mixtures while at the same time promoting ecosystem complexity and resilience.[8,16,12]

Testing these theories requires accurate and detailed information regarding the productivity and regeneration dynamics across the range of growing conditions that exists in these stands. After twenty years, composition and growth data from the permanent plot network in the AFERP experiment currently exists at a relatively coarse scale, and some preliminary work has been done using the 10-year data to generalize regarding the impact of harvest spatial pattern on overall stand growth[2,17] and the overall spatial patterning of regeneration throughout these stands[14]. So far, however, none of these analyses have included a detailed assessment of productivity and regeneration dynamics within the harvest gap environment, despite the fact that harvest gaps now make up to 20% of total stand area and exhibit high variability in composition and structure.

In order to fully assess the success of these treatments in balancing management goals there remains a need, therefore, for a detailed characterization of the spatiotemporal patterns and physiological drivers of species distribution, survival, growth, and competitive dynamics in regeneration and retention layers within harvest gaps. These assessments will be crucial to determining the efficacy of variable retention expanding gap treatments in meeting productivity and regeneration goals, as well as in aiding the prediction of composition and growth in the development of complex stands, and therefore more broadly of assessing the role of these variable retention NDBS approaches for the broader Northern Forest landscape.

Research Approach and Methodology:

By design, the AFERP study has a strong spatial pattern, with carefully regulated harvest gaps being a critical focus of each treatment prescription. Unlike most managed-gap studies, AFERP also prescribes retention of large trees within expanding gap harvest in order to enhance structural complexity and multifunctionality.[7,9] The AFERP experiment consists of nine 10 hectare research areas, three in which 20% of the area is harvested using 0.2 ha expanding gaps with a 10-year regeneration period and 10% BA permanent retention, three in which 10% of the area is harvested using 0.1 ha expanding gaps with a 20-year regeneration period and 10% BA permanent retention, and three controls. Within each research area, a permanent plot network of 15-20 nested overstory, sapling, and regeneration plots have been monitored every 5 years since 1995. We will capitalize on and extend these existing data through a census of retention trees and intensive sampling of regeneration across a range of growing conditions within harvest gaps.

Retention tree volume growth will be estimated using dendrochronological analysis of increment cores and height models developed from existing measurements. Current leaf area will be estimated from sapwood basal area measurements on cores,[6] and crown shape and projection area will be estimated using a combination of existing aerial imagery[21] and direct measurements. Physiological response to crown release in terms of water use efficiency (WUE), net photosynthesis (Anet), and stomatal conductance (gs) will be measured by analyzing 18O and 13C concentrations in annual growth rings 3 years pre- and post-harvest.[3,4,11]

Regeneration will be sampled by identifying 30 focal trees each of 4 species (A. rubrum, T. canadensis, P. strobus, and A. balsamea). These will be height-dominant trees in pre-existing pilot study plots stratified by species and spatial location within harvest gaps. Focal trees will be the center of new plots in which all stems will be measured and mapped. Spatial position, light measurements, and depth to seasonally high water table will be taken at plot center. Stem cookies will be collected from focal trees every 0.5 meter and random branch sampling conducted to obtain leaf area and biomass estimates.[5] Dendrochronological analysis will be used to reconstruct growth and physiological response to release will be measured by analyzing 18O and 13C concentrations in annual growth rings. Null hypotheses will be tested using hierarchical mixed-effects models.

Expected Outcomes and Products:

A detailed analysis of within-gap growth pattern and process will uncover the effects of spatial relationships in harvest gaps on productivity and composition in retention and regeneration layers, producing material for at least 5 peer-reviewed publications. Moreover, when combined with permanent plot data, this project will allow a more detailed and accurate overall assessment of these treatment impacts on stand productivity and compositional dynamics, providing the informational basis to refine predictive models of stand development and more adequately assess the efficacy and role of variable retention expanding gap NDBS systems in the Northern Forest. At its broadest scope, this project makes significant inroads exploring the balance between managing for complexity to maintain ecosystem resilience and reliably managing stand productivity and development.

Project Budget

| Expense | Year 1 | Year 2 | Total |
| --- | --- | --- | --- |
| 1 PI summer salary (Seymour) | $7,913 |  | $7,913 |
| 2 Graduate student supplement | 15,000 | $17,000 | 32,000 |
| 3 Travel | 2,000 | 1,000 | 3,000 |
| 4 Field equipment and office supplies | 2,000 |  | 2,000 |
| 5 Analysis | 20,000 |  | 20,000 |
| Total request from NSRC | $48,913 | 18,000 | $66,913 |

Budget Justification

1  -  Project oversight by PI (2 weeks + 51% overhead)

2  - M.S. graduate student stipend supplements ($500/month for twelve month, plus an  addition full support for 4 months at $2000/month) and PhD graduate student stipend ($750/ month for twenty-four months)

3 – Daily travel to and from study sites; presentations at regional meetings

4 – Miscellaneous field supplies and equipment

5 – Wood mounts for cores, labor for sample preparation, and oxygen and carbon isotope fractionation analysis for samples. Collect 4 samples from 30 individuals for 3 species in both retention and regeneration layers. Estimated cost for analysis of oxygen samples: $16. Estimated cost for analysis of

______________________________________________________________________________

Literature Cited

1.

Arseneault, J. E. & Saunders, M. R. Incorporating canopy gap-induced growth responses into spatially implicit growth model projections. Ecological Modelling 237-238, 120–131 (2012).

2.

Arseneault, J. E., Saunders, M. R., Seymour, R. S. & Wagner, R. G. First decadal response to treatment in a disturbance-based silviculture experiment in Maine. Forest Ecology and Management 262, 404–412 (2011).

3.

Bladon, K. D., Silins, U., Landhäusser, S. M., Messier, C. & Lieffers, V. J. Carbon isotope discrimination and water stress in trembling aspen following variable retention harvesting. Tree physiology 27, 1065–1071 (2007).

4.

Brooks, J. R. & Mitchell, A. K. Interpreting tree responses to thinning and fertilization using tree-ring stable isotopes. New Phytologist 190, 770–782 (2011).

5.

Gregoire, T. A. & Valentine, H. T. Sampling Strategies for Natural Resources and Environment. (Chapman-Hall, 2008).

6.

Guiterman, C. H., Seymour, R. S. & Weiskittel, A. R. Long-Term Thinning Effects on the Leaf Area of Pinus strobus L. as Estimated from Litterfall and Individual-Tree Allometric Models. Forest Science 58, 85–93 (2012).

7.

Gustafsson, L. et al. Retention Forestry to Maintain Multifunctional Forests: A World Perspective. BioScience 62, 633–645 (2012).

8.

Holling, C. S. Resilience and Stability of Ecological Systems. Annual Review of Ecology and Systematics 4, 1–23 (1973).

9.

Lindenmayer, D. B. et al. A major shift to the retention approach for forestry can help resolve some global forest sustainability issues: Retention forestry for sustainable forests. Conservation Letters 5, 421–431 (2012).

10.

Lindenmayer, D. B. & Franklin, J. F. in Conserving Forest Biodiversity: A Comprehensive Multiscaled Approach 55–71 (Island Press, 2002).

11.

McCarroll, D. & Loader, N. J. Stable isotopes in tree rings. Quaternary Science Reviews 23, 771–801 (2004).

12.

Messier, C., Puettmann, K. J. & Coates, K. D. Managing Forests as Complex Adaptive Systems. (Routledge, 2013).

13.

North, M. P. & Keeton, W. S. in Patterns and Processes in Forest Landscapes (Lafortezza, R., Sanesi, G., Chen, J. & Crow, T. R.) 341–372 (Springer Netherlands, 2008). at <http://link.springer.com/chapter/10.1007/978-1-4020-8504-8_19>

14.

Olson, M. G. & Wagner, R. G. Factors affecting species richness of tree regeneration in mixed-wood stands of central Maine. Journal of Vegetation Science 22, 303–311 (2011).

15.

Pickett, S. T. A. & White, P. S. The Ecology of Natural Disturbance and Patch Dynamics. (Academic Press, 1985).

16.

Puettmann, K. J., Coates, K. D. & Messier, C. C. A critique of silviculture managing for complexity. (Island Press, 2009). at <http://proxy2.hec.ca/login?url=http://site.ebrary.com/lib/hecm/Doc?id=10511990>

17.

Saunders, M. R. & Arseneault, J. E. Potential Yields and Economic Returns of Natural Disturbance-Based Silviculture: A Case Study from the Acadian Forest Ecosystem Research Program. Journal of Forestry 111, 175–185 (2013).

18.

Seymour, R. S. & Hunter, M. L. in Managing Biodiversity in Forest Ecosystems 22–61 (Cambridge University Press, 1999).

19.

Seymour, R. S. Integrating Natural Disturbance Paramters into Conventional Silvicultural Systems: Experience From the Acadian Forest of Northeastern North America. in Balancing Ecosystem Values: Innovative Experiments for Sustainable Forestry (Peterson, C. E. & Maguire, D. A.) 41–48 (US Department of Agriculture, Forest Service, Pacific Northwest Research Station, 2005).

20.

Seymour, R. S., White, A. S. & demaynadier, P. G. Natural disturbance regimes in northeastern North America—evaluating silvicultural systems using natural scales and frequencies. Forest Ecology and Management 155, 357–367 (2002).

21.

Wang, L., Gong, P. & Biging, G. S. Individual tree-crown delineation and treetop detection in high-spatial-resolution aerial imagery. Photogrammetric Engineering and Remote Sensing 70, 351–358 (2004).

# Curriculum Vita - Robert S. Seymour

# School of Forest Resource, College of Natural Sciences, Forestry, and Agriculture

211 Nutting Hall University of Maine; Orono, ME  04469-5755

(207) 581-2860   FAX: (207) 581-2875

Email: rseymour@maine.edu   Web page:www.forest.umaine.edu/facstaff/facstaff_pages/seymour/

# Education:

Ohio State University (BS, 1974); Yale School of Forestry and Environmental Studies (MF 1976, PhD 1980)

Professional Experience:

Curtis Hutchins Professor of Forest Resources (Quantitative Silviculture) 1987-Present (tenured 1990).    Research Interests: canopy structure-stemwood growth relationships; development of managed and old-growth stands; growth and yield modeling; green certification

Awards:

Pew Fellow, Conservation and the Environment, 1995-98.

Outstanding Public Service Award, College of Natural Sciences, Forestry, and Agriculture, 2002-03.

# G. Peirce and Florence Pitts Webber Outstanding Forestry Teaching Award, 2004-05

# Fellow, Society of American Foresters, 2008

# First NSRC Profiled Researcher (2009)

Selected Publications -- Journal Articles, Research Bulletins, and Book Chapters

MacLean, D.A., R.S. Seymour, M.K. Montigny & C. Messier. 2009. Allocation of conservation efforts over the landscape: the TRIAD approach. P. 283-303 In: Villard, M.A. and Jonsson, B.G.  Setting Conservation Targets for Managed Forest Landscapes. Cambridge Univ. Press, NY, N.Y.  411 p.

# DeRose, R.J. and R.S. Seymour. 2009.  The effect of site quality on growth efficiency of upper crown class Picea rubens and Abies balsamea in Maine, USA. Can. J. For. Res. 39:777-784.

Hofmeyer, P.V., R.S. Seymour and L.S. Kenefic. 2009.  Influence of soil site class on growth and decay of northern white-cedar in Maine.  North. J. Appl. For. 26(2):68-75.

Fraver, S., A.S. White, and R.S. Seymour. 2009 Patterns of natural disturbance in an old-growth landscape of northern Maine, USA.  Journal of Ecology 97: 289–298.

Moores, A.R., R.S. Seymour, and L.S. Kenefic.  2007.  Height development of shade-tolerant conifer saplings in multi-aged Acadian forest stands. Can. J. For. Res. 37:2715-2723.

Seymour, R.S.  2007.  Low-density management of white pine crop trees: a primer and short-term research results. Northern Journal of Applied Forestry: 24(4):301-306.

Fraver, S., R.S. Seymour, J.H. Speer, and A.S. White.  2007. Dendrochronological reconstruction of spruce budworm outbreaks in northern Maine, USA.   Can. J. For. Res. 37:523-529.

Seymour, R.S., J.Guldin, D.Marshall, and B.Palik 2006. Large-scale, long-term silvicultural experiments in the United States. Allgemeine Forst-und Jagdzeitung 177:104-112

Seymour, R.S. and L.S. Kenefic. 2002. Influence of age on growth efficiency of Tsuga canadensis and Picea rubens trees in mixed-species, multi-aged northern conifer stands.  Can. J. For. Res. 32:2032-2042.

Seymour, R.S., A.S. White and P.G. de Maynadier. 2002. Natural disturbance regimes in northeastern North America – Evaluating silvicultural systems using natural scales and frequencies. Forest Ecology and Management 155:357-367.

Seymour, R. S. and M.L. Hunter, Jr.  1999.  Principles of Ecological Forestry.  Ch.  2 (p. 22-61) In: Managing Biodiversity in Forest Ecosystems. M.L. Hunter, Jr., editor.  Cambridge Univ.  Press. 698 p.

Seymour, R. S.  1995.  The Northeastern Region. p. 31-79 In: Regional Silviculture of the United States, Ed. 3.  Ed. J. W. Barrett.  Wiley and Sons, N. Y.  643 p.

Seymour, R. S. 1992. The red spruce-balsam fir forest of Maine: Evolution of silvicultural practice in response to stand development patterns and disturbances. Ch. 12 (p. 217-244) In: Kelty, M. J., Larson, B. C. and Oliver, C. D., eds.  The Ecology and Silviculture of Mixed-species forests. A festschrift for David M. Smith.  Kluwer Publishers, Norwell, MA.

Shawn Fraver C.V.

Education

- Ph.D. 	Forest Resources, University of Maine (2004)

- M.S. 	Forestry, Restoration Ecology Program, North Carolina State University

- B.S. 	Biology (Ecology Emphasis), The Pennsylvania State University

Recent Professional Experience

- 2013-present Assistant Professor, School of Forest Resources, Univ. of Maine, Orono

- 2013 Research Associate Professor, Dept. Forest Resources, Univ. Minnesota, St Paul.

- 2007-2012 Research Ecologist, USFS, Northern Research Station, Grand Rapids, MN

- 2004-2006 Post-Doctoral Researcher, Dept. of Natural Sciences, Mid Sweden Univ., Sundsvall, Sweden.

Selected Relevant Publications

Fraver, S., A.W. D’Amato, J.B. Bradford, B.G. Jonsson, M. Jönsson, and P.-A. Esseen. In press. Tree growth and competition in an old-growth Picea abies forest of boreal Sweden: Influence of tree spatial patterning. Journal of Vegetation Science.

Fraver, S., A.M. Milo, J.B. Bradford, A.W. D’Amato, L. Kenefic, B.J. Palik, C.W. Woodall, and J. Brissette. 2013. Woody debris volume depletion through decay: Implications for biomass and carbon accounting. Ecosystems 16(7): 1262-1272.

Aakala T., S. Fraver, A.W. D’Amato, and B.J. Palik. 2013. Influence of competition and age on tree growth in structurally complex old-growth forests in northern Minnesota, USA. Forest Ecology and Management 308: 128-135.

Silver, E.J., A.W. D’Amato, S. Fraver, B.J. Palik, and J.B. Bradford. 2013. Structure and development of old-growth, unmanaged second-growth, and extended rotation Pinus resinosa forests in Minnesota, USA. Forest Ecology and Management 291: 110-118.

Fraver, S. and B.J. Palik. 2012. Stand and cohort structures of old-growth Pinus resinosa-dominated forests of northern Minnesota, USA. Journal of Vegetation Science 23: 249-259.

Aakala, T., S. Fraver, B.J. Palik, and A.W. D'Amato. 2012. Spatially random mortality in old-growth red pine forests of northern Minnesota. Can. J. For. Research 42: 899-907.

Svoboda, M., P. Janda, T. Nagel, S. Fraver, J. Rejzek, and R. Bače. 2012. Disturbance history of an old-growth sub-alpine Picea abies stand in the Bohemian Forest, Czech Republic. Journal of Vegetation Science 23: 86-97.

Fraver, S., T. Jain, J.B. Bradford, A.W. D’Amato, D. Kastendick, B.J. Palik, and D. Shinneman. 2011. The efficacy of salvage logging in reducing subsequent fire severity in conifer-dominated forests of Minnesota, USA. Ecological Applications 21(6): 1895-1901.

Fraver, S., J.B. Bradford, and B.J. Palik. 2011. Improving tree age estimates derived from increment cores: a case study of Pinus resinosa. Forest Science 57:164-170.

D’Amato, A.W., J. Bradford, S. Fraver, and B.J. Palik. 2011. Forest management for mitigation and adaptation: insights from long-term silvicultural experiments. Forest Ecology and Management 262: 803-816.

Fraver, S., A.S. White, and R.S. Seymour. 2009. Natural disturbance in an old-growth landscape in northern Maine, USA. Journal of Ecology 97: 289-298.

Fraver, S. and A.S. White. 2005. Disturbance dynamics of old-growth Picea rubens forests of northern Maine. Journal of Vegetation Science 16: 597-610.

Fraver, S. and A.S. White. 2005. Identifying growth releases in dendrochronological studies of forest disturbance. Canadian Journal of Forest Research 35(7): 1648-1656.