AFERP to do list (2012-2013)

- Remap all plots using azimuth from plot center to tree and remeasure distance

  - Currently there are many inconsistencies in location data. Some azimuths were taken from plot center others from the tree. Some location data are just wrong!

- Mapping of Retention trees

  - Many of the retention trees have been mapped but not all

| RA | Total # RT in database | Measured in INV 4 | GPS points |
| --- | --- | --- | --- |
| 1 | 433 | 160 | 114 |
| 2 | 107 | 100 | 96 |
| 5 | 127 | 113 | 108 |
| 6 | 369 | 349 | 300 |
| 7 | 63 | 63 | 62 |
| 9 | 204 | 184 | 144 |

- Resolve species for all retention trees, overstory trees, saplings

  - In the past there have been many errors in tree identification. An effort has been made in INV 4 to resolve many of these but some problems still remain.

  - Once the species identification problems are fully resolved the database can be updated and the species field removed from the inventory data.

- Maintenance

  - Refresh paint on gridlines.

  - Finish remarking retention trees.

  - Some plots need rebar and/or rebar caps replaced.

- Complete digitizing of AFERP records

  - To date all records from 2000 to present have been scanned as pdfs and organized under AFERP > Data > AFERP Scanned data

  - Ensure that all datasheets from past years are scanned and legible. Convert scanned tiffs and any other formats to pdf.

- Database

  - Light measurements- In the interest of data management it may be better to store raw Above and Below readings in the light data, rather than calculated values.

  - Overstory, Retention, and Saplings- As noted above static attribute fields should be removed from measurement tables once species problems are resolved.

  - Forms- We toyed with the idea of entering data directly into the database, rather than entering in Excel and importing. The beginnings of an overstory  data entry form are in the database but needs completion.

  - Reports- The datasheets have been improved and could use some more work.

  - Missing data- Much of the data from INV3 was not imported. Much of that has been resolved, but I have not been able to find many of the light measurements from INV3. It would be a good idea to run some queries to check for missing data and look through the Excel spreadsheets and possibly scanned datasheets for any data that still needs to be brought into the database.

  - Since updating the database, queries were retained but not updated, primarily due to table and field name changes. It may be useful to update these queries.

- Continue updating the AFERP protocol.

  - Many updates have been completed but several sections remain to be written (i.e., 9. Gap Vegetation and Environment and 10. Harvest Inventory).

  - There are some persistent formatting flaws.

  - Currently one of the major flaws in the protocol is the inability to link harvest removals to individual trees. Pre- and post-harvest data collection should involve recording the id code for trees removed and/or damaged.

  - Appendix A- need to update maps.

  - Appendix C- Retention tree maps need to be created and inserted.

  - Resolve uncertainties in protocol. Examples:

    - Protocol uses breast height at 1.3 m but it is likely that many of the measurements were taken at 1.37

    - Some items uses magnetic north and some use true north